## Execution Summary
Metric | As reported in PDF summary | Recount from PDF test case table
Total Test Cases | 20 | 20
Executed | 20 | 20
Passed | 18 | 17
Failed | 1 | 2
Blocked | 1 | 1
Not Executed | 0 | 0
The PDF's summary (18/1/1) differs from its own test case table (17/2/1). Both are shown; nothing has been altered. Recount is based on the 'Test Cases' sheet in this workbook (statuses copied from the PDF; TC014 = "Pass (Bug Observed)" counted as Pass).

## Defect Summary
Severity | Count (from Bugs sheet) | Count reported in PDF
Critical | 0 | 0
High | 2 | 2
Medium | 6 | 6
Low | 3 | 3
Total | 11 | 11

## Testing Types
Testing Type | Test Cases (from PDF table) | Count
Functional Testing | TC008, TC013, TC014, TC016, TC017 | 5
Validation Testing | TC002, TC003, TC004, TC005, TC006, TC007 | 6
Negative Testing | TC009, TC010, TC011, TC015 | 4
UI Testing | TC001, TC012 | 2
API Testing | TC018, TC019, TC020 | 3

## Key Findings
Area | Finding
Overall | The PDF concludes that core login functionality works as expected; the identified issues relate mainly to OTP handling, UI behavior and API response consistency.
Mobile number validation | Empty, short, wrongly-starting, over-length, alphabetic and special-character inputs were handled (TC002-TC007, TC020). The invalid-start message has a grammar issue (BUG001).
Login / session | Valid OTP login succeeded, and the session persisted across refresh and a new tab (TC013). Logout invalidated the session and protected actions redirected to login (TC014).
Logout / cart | Inconsistent cart count was observed after logout (TC014, BUG009).
OTP request limit | After the limit was reached, the app still let users proceed to the OTP screen with no OTP sent (TC011 Fail, BUG007); limit reset time, remaining attempts and cooldown behavior are not communicated (BUG003, BUG004, BUG006). Generation and verification attempts share one limit counter (BUG010).
OTP expiry | No OTP validity timer is shown (BUG002); no specific expiry message was observed (BUG005, Needs Confirmation).
API behavior | The OTP generation request returned HTTP 200 without exposing the OTP (TC018). When the request limit was exceeded, the API returned HTTP 200 with "status": 400 in the body (TC019 Fail, BUG011).
Blocked test | TC015 (rapid clicks on Generate OTP) was Blocked because the app moved to the OTP page immediately after the first click.
Dashboard greeting | A first-time user sees a 'welcome back' style greeting (BUG008).
Count discrepancy | The PDF summary reports 18 Passed / 1 Failed / 1 Blocked; its test case table shows 17 / 2 / 1.

## Test Cases
Test Case ID | Test Type | Status
TC001 | UI Testing | Pass
TC002 | Validation Testing | Pass
TC003 | Validation Testing | Pass
TC004 | Validation Testing | Pass
TC005 | Validation Testing | Pass
TC006 | Validation Testing | Pass
TC007 | Validation Testing | Pass
TC008 | Functional Testing | Pass
TC009 | Negative Testing | Pass
TC010 | Negative Testing | Pass
TC011 | Negative Testing | Fail
TC012 | UI Testing | Pass
TC013 | Functional Testing | Pass
TC014 | Functional Testing | Pass (Bug Observed)
TC015 | Negative Testing | Blocked
TC016 | Functional Testing | Pass
TC017 | Functional Testing | Pass
TC018 | API Testing | Pass
TC019 | API Testing | Fail
TC020 | API Testing | Pass

## Bugs
Bug ID | Severity | Status
BUG001 | Low | Open
BUG002 | Medium | Open
BUG003 | Medium | Open
BUG004 | Low | Open
BUG005 | Medium | Needs Confirmation
BUG006 | Medium | Open
BUG007 | High | Open
BUG008 | Low | Open
BUG009 | Medium | Open
BUG010 | High | Open
BUG011 | Medium | Open